## SLOC
Team Number: | 8
Week: | 1
Program Size (SLOC) | Actual
Base | TBD
Added | 0
Deleted | 0
Modified | 0
Reused | 0
From COTS | 0
Total New SLOC | 0

## COTS
List of third-party components being considered for use in the system as of 09/18/2020
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
Sendbird | Chat, Audio, Video Functionalities | N/A |  | x
Twillo | Chat, Audio, Video Functionalities | N/A |  | x
Mirrorfly | Chat, Audio, Video Functionalities | N/A |  | x
Vonage | Chat, Audio, Video Functionalities | N/A |  | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Draft and polish win conditions for the referral system and chat system
2 | Explore source code that spans across multiple APIs and MongoDB
3 | Determine whether or not to include the recommendation system as part of project scope
4
5
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Get access to the Nuleep Codebase
2 | Access to Azure DevOps
3
4
5
C. | List your accomplishments from the previous week
1 | Establish stack channel for communication with Nuleep Team
2 | Set up internal Google drive and weekly meeting schedule
3
4
5
6
7
8