## Risk
Top Project Risks as of 09/18/2020
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed? | No. of Weeks Active
This Week | Last Week
3 | N/a | Lack of developer knowledge regarding React Native on how to implement an app | Lack of developer knowledge | Learn and research about React Native and build prototypes | 10 | 8 | 80 |  | 1
2 |  | Lack of clear understanding of the requirements | Lack of developer knowledge and a lack of client's exact technical needs | Lack of experience from the team members who are acting as the requirements engineers | 7 | 9 | 63 |  | 1
1 |  | Lack of clear understanding of the Win-Conditions | Lack of client interaction | Conducting a Win-Condition negotiation with the client | 5 | 10 | 50 |  | 1

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1
2
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1
2
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | The Win-Conditions are ambiguous | Do more research and discuss with clients about Win-Conditions
2
3
4
5