## SLOC
Team Number: | 8
Week: | 2
Program Size (SLOC) | Actual
Base | TBD
Added | 0
Deleted | 0
Modified | 0
Reused | 0
From COTS | 0
Total New SLOC | 0

## COTS
List of third-party components being considered for use in the system as of 09/18/2020
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
Twilio | Chat, Audio, Video Functionalities | N/A |  | x
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References
Sendbird | High license fee
Mirrorfly | Unwanted by the client
Vonage | Unwanted by the client

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Become more familiar with React Native and the packages currently used
2 | Explore the codebase that we just got access to
3 | Successfully build the existing project
4 | Connect to the client's AWS servers
5
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Obtain Twilio license
2 | Approval from the client to finalize the UI components/prototype for the chat system
3 | Formal project kick-off
4
5
C. | List your accomplishments from the previous week
1 | Get access to the Nuleep Codebase
2 | Access to Azure DevOps
3 | Renegotiate win win conditions, only do the chat system
4 | Clarified win-win conditions with the stakeholders
5
6
7
8